## Worksheet
QMSR 90-Day Implementation Roadmap
Editable preparation aid — not an FDA form or certification tool. Complete and review against applicable requirements.
Target period | Workstream | Suggested owner | Requirement reference | Evidence reference | Gap or task | Risk priority | Interim control | Action | Status | Effectiveness evidence
Days 1–30 | Scope and applicability | Quality / regulatory | 21 CFR Part 820 |  | Confirm covered devices and activities |  |  |  | Open
Days 1–30 | Baseline record samples | Quality / engineering |  |  | Sample release, change and complaint |  |  |  | Open
Days 31–60 | Requirements-risk-V&V | Engineering / quality |  |  | Close traceability and evidence gaps |  |  |  | Open
Days 31–60 | Supplier controls | Operations / quality |  |  | Evaluate critical outsourced activities |  |  |  | Open
Days 31–60 | Controlled workflow updates | Process owners |  |  | Implement controls and training |  |  |  | Open
Days 61–90 | Effectiveness evaluation | Quality |  |  | Sample new records and recurrence |  |  |  | Open
Days 61–90 | Retrieval rehearsal | Quality / regulatory | CP 7382.850 |  | Follow linked evidence across processes |  |  |  | Open
Immediate when warranted | Containment and reporting | Responsible safety / regulatory functions |  |  | Assess urgent risks and applicable obligations |  |  |  | Open
Cahir MedTech · © Cahir AI LLC 2026